## Sheet1
Defect ID | Severity | Priority | Status | Assigned To | Assigned to Team | Defect Type | Detected By | Summary | Description | Detected in Cycle | Detected in Release | Detected on Date | Planned fix date
6991 | 3 – Medium | P3 – Medium | Open | kamlakar_choudhary | ITC Infotech | Application | prashant_dwivedi | MC label printer is not working correctly | Test Instance[38470] : [1]Manual Production Change with APRISO ME T&T HH [with MC label printing only] scanned QA BAR code has suffix MA following with url. MA suffix to be removed | BO1490070 Indonesia Fixed Deployment SIT | BO1490070 Indonesia Fixed Deployment SIT | 2024-08-13
6989 | 3 – Medium | P3 – Medium | Closed | abhishek_ash1 | ITC Infotech | Application | prashant_dwivedi | In Production Change traction Execution Automatic Batch ID Generation is not working. | In Production Change traction Execution Automatic Batch ID Generation is not working. | BO1490070 Indonesia Fixed Deployment SIT | BO1490070 Indonesia Fixed Deployment SIT | 2024-08-09 | 2024-08-12
6985 | 2 – High | P2 – High | Closed | rishabh_chandan | ITC Infotech | Coding Defect | ramesvar_vasudevan | Unable to perform Destroy All transactaion in ME HHT | Test Instance[38473] : [1]Destroy a previously registered Case in ME area (Destroy All transaction on APRISO ME T&T HH) ME HTT shows "Arthimetic overflow error converting expression to data type int" error while performing destroy function | BO1490070 Indonesia Fixed Deployment SIT | BO1490070 Indonesia Fixed Deployment SIT | 2024-08-07 | 2024-08-09
6983 | 3 – Medium | P3 – Medium | Closed | sudip_nanda | ITC Infotech | Authorisation | prashant_dwivedi | Error on triggering Email from FSS3 to External Email id | Test Instance[38468] : [1]Notification of Material Master Data issue following update from TaO ECC we are trigrring mail from FSS to external mail ID but its getting error. we are inform to Local team for configuration, local team person is working on SMTP configuration. | BO1490070 Indonesia Fixed Deployment SIT | BO1490070 Indonesia Fixed Deployment SIT | 2024-08-05 | 2024-08-07