## SIT Entry Criteria
| SIT DATE : 5 Aug - 23 Aug |  |  |  | ITC
| BUILD | ITC |  |  | COMPLETE
Sl. No | Description | Responsible Team | Responsible Owner | Critical End Date | RAG Status | Current Comments(Ensure comments are up to date with CURRENT status to reflect correct RAG status to GREEN)
1. Build and FUT for all relevant systems exit has been signed off
1.01 | FUT script review/sign off | ITC |  |  | NOT APPLICABLE
1.02 | FUT Execution Completion | ITC |  |  | NOT APPLICABLE
1.03 | FUT Defect Closure | ITC |  |  | NOT APPLICABLE
1.04 | FUT Closure Report Preparation | ITC |  |  | NOT APPLICABLE
1.05 | FUT Exit and Closure Report Sign Off | BAT |  |  | NOT APPLICABLE
2 - SIT scope signed off
2.01 | Functional Specification reviewed and approved | BAT | Sandra | 2024-07-01 | COMPLETE | Sandra will share SIT sceanrios on 1-Jul
2.02 | Test Scope Confirmation and sign off | BAT | Sandra | 2024-07-01 | COMPLETE | Scenario can be still [potentially] modified next week – after METS Simulator training.
3 - Environment availability for all relevant systems including interfaces
3.01 | ECC | ITC | Ajay/Shaik | 2024-07-09 | COMPLETE
3.02 | EIB - PI | Integration | Rafael/Sudarson | 2024-07-19 | COMPLETE | 1. Demand not approved : to move TR To test environment DMND0007060
3.03 | M-WSS | Honeywell |  | 2024-07-19 | GREEN | 1. Basic configuration of HHT - Local IT 2. Honey well to setup enviornment - CR number
3.04 | FSS 3 | ITC | Sudip | 2024-07-05 | COMPLETE
3.05 | Honeywell HHT ME | ITC | Sudip | 2024-07-19 | GREEN | 1. Basic configuration of HHT - Local IT 2. Honey well to setup enviornment - CR number 3. PArticipant ID and local ID to ITC
3.06 | SAP ATTP - New Scope ( T62) | ITC |  | 2024-06-06 | COMPLETE
3.06 | SAP ATTP - Existing Scope(T62) | ITC | Sudip | 2024-07-05 | COMPLETE
3.07 | Moviliser Cloud | ITC |  | 2024-06-06 | NOT APPLICABLE
3.08 | OER | ITC | Veerababu | 2024-07-19 | GREEN | To confirm with BAT
3.09 | AxWay | Integration | Rafael/Sudarson | 2024-07-19 | GREEN
3.09A | SAT | SAT team |  | 2024-07-19 | GREEN | To confirm with BAT
3.10 | Line system simulator | ITC | Sudip | 2024-07-05 | COMPLETE | Conifgured
3.11 | Apriso HHT - ME | ITC |  | 2024-06-06 | NOT APPLICABLE
3.12 | TaO to FSS3 | ITC | Sudip / Rafael | 2024-07-19 | GREEN | Connectivity Test Completed. MATMAS and LOIPRO message sent successfully with sample data
3.13 | FSS3 to GATE | ITC | Sudip / Rafael | 2024-07-19 | GREEN | Option 1 : Require a SKU to perform connecitivy test easily Option 2 : Connectivity test with sample data. ETA 12-Jul
3.14 | FSS3 to Osapiens | ITC |  |  | NOT APPLICABLE
3.15 | Osapiens to CRPT | Osapiens |  |  | NOT APPLICABLE
3.16 | GATE to Vault | ITC | Sudip / Rafael | 2024-07-19 | GREEN | Option 1 : Require a SKU to perform connecitivy test easily Option 2 : Connectivity test with sample data. ETA 12-Jul
3.17 | Vault to SAT | Inextor | Sudip / Rafael | 2024-07-19 | GREEN | Scope not clear yet
3.18 | Liz to MC level Printer | ITC | Sudip / Rafael | 2024-07-19 | GREEN | Connectivity test with sample data. ETA 12-Jul
3.19 | FSS3 to METS Simulator | ITC | Sudip / Rafael | 2024-07-19 | GREEN | Action on BAT. Training required.
3.20 | GMES to FSS3 | GMES |  |  | NOT APPLICABLE
3.21 | TaO to GMES | GMES |  |  | NOT APPLICABLE
3.22 | GMES to STS | GMES |  |  | NOT APPLICABLE
3.23 | TaO to ATTP | ITC | Sudip / Rafael | 2024-07-12 | GREEN | Master Data team to trigger Idoc
3.24 | ATTP to OER | ITC | Sudip / Rafael | 2024-07-19 | GREEN | Action on BAT : Scope of OER
3.25 | FSS3 to ATTP | ITC | Sudip / Rafael | 2024-07-19 | GREEN | Axway and CPI. Test the connectivity with sample data - 8-Jul-24
3.26 | STS to MC labeler Printer | STS |  |  | NOT APPLICABLE
3.27 | METS to Outer Label Printer | METS | Sudip / Rafael | 2024-07-19 | GREEN | Scope not clear yet
3.28 | GMES HH availability | Local IT |  |  | NOT APPLICABLE
3.29 | STS to ATTP | STS |  | 2024-07-19 | GREEN | To confirm with BAT
3.30 | STS to TaO | STS | Sudip / Rafael | 2024-07-19 | GREEN | To confirm with BAT
3.31 | FSS3 to STS | ITC | Sudip / Rafael | 2024-07-19 | GREEN | To confirm with BAT
4 -Testing collateral ready for all relevant systems
4.02 | Test Script Preparation | BAT | Sandra | 2024-07-01 | COMPLETE
4.03 | Test Script Review and Sign Off | BAT | Sandra | 2024-07-01 | COMPLETE
4.04 | Test Plan Schedule Preparation | Test Management | Ramesvar Giri Vasudevan | 2024-07-19 | COMPLETE
4.05 | Tester Allocation for defined Test Scenario | Test Management | Ramesvar Giri Vasudevan | 2024-07-19 | COMPLETE
4.06 | HPQC Test Script Readiness | Test Management | Ramesvar Giri Vasudevan | 2024-07-19 | COMPLETE
5 - Readiness of testing data for all relevant systems
5.01 | Data Requirement Confirmation | ITC | Ajay/Shaik | 2024-07-19 | COMPLETE
5.02 | Data readiness plan | ITC | Ajay/Shaik | 2024-07-19 | COMPLETE
5.03 | Data Setup Completion | ITC | Ajay/Shaik | 2024-07-19 | COMPLETE
6. Test resources available and ready (roles/access) with functional knowledge
6.01 | Testers Confirmation | ITC | ITC | 2024-07-19 | COMPLETE
6.02 | Testers Test System Access | Test Management | Ramesvar Giri Vasudevan | 2024-07-19 | COMPLETE
6.03 | Testers Test System Access confirmation | Test Management | Ramesvar Giri Vasudevan | 2024-07-19 | COMPLETE
6.04 | Functional knowledge sharing with Testers | Test Management | Ramesvar Giri Vasudevan | 2024-07-19 | COMPLETE
7- Test resource HPQC access with knowledge
7.01 | Testers HPQC Access | Test Management | Ramesvar Giri Vasudevan | 2024-07-19 | COMPLETE
7.02 | Testers HPQC Access confirmation | Test Management | Ramesvar Giri Vasudevan | 2024-07-19 | COMPLETE
7.03 | Testers HPQC Training | Test Management | Ramesvar Giri Vasudevan | 2024-07-19 | COMPLETE
8 - SIT Kick Off Completion
8.01 | SIT Kick off confirmation email/call | Test Management | Ramesvar Giri Vasudevan | 2024-07-19 | COMPLETE
8.03 | Progress call and Command Centre Arrangement | Test Management | Ramesvar Giri Vasudevan | 2024-07-19 | COMPLETE
8.02 | SIT Defect Monitoring Call setup | Test Management | Ramesvar Giri Vasudevan | 2024-07-19 | COMPLETE

## ADO (hidden)
CR | Features | Work Item Onwer | Build Owner | Show stopper | Status /Remarks | Owner | Itreation | FUT | SIT | RT Yes /No | PVT /Yes or NO | Comments
1252457 | BO | Augustow Re-Platforming PL01, PL04, PL19 | NA
1346343 |  | AGW re-platforming - deployment timelines change | NA | CR1393197
1289401 |  | Augustow re-platforming - analytics effort | TCS | CR1086453
1289445 |  | Augustow re-platforming - Honeywell effort | Honeywell
1289428 |  | Augustow re-platforming - Integration effort | Rafel
1289466 |  | Augustow re-platforming - Movilitas effort | Movilitas
1289419 |  | Augustow re-platforming - Orchestration effort | TCS Orchestario
1231088 |  | Augustow - Re-Platforming - TCS fixed bid cost | NA
1231088 | 1307718 | Augustow ATTP Standard Deployment | TCS
1231088 | 1324795 | Augustow LE Standard Deployment | TCS
1231088 | 1324805 | Augustow ME Standard Deploymnet | TCS
797925 | 820296 | Allow / Block PDA and Delivery Payload Change based upon Portal Status - Boards (visualstudio.com) |  | Yes | Dependent with 820328 - Need to check With Lukasz - Tentative | Lukasz S | 23'06
797925 | 820328 | Allow / Block PGI based upon Portal Status - Boards (visualstudio.com) |  | Yes | Dependent with 8202967- Need to check With Lukasz | Lukasz S | 23'04
1261918 |  | FSS3: send EPCIS Storing event to ATTP 3.0 for REWORK PO AGW GAP - Boards (visualstudio.com) |  | Yes | to be deployed on May . | Tomasz D | 23'08
1263781 | 1229000 | ATTP3.0 - KSA production in EU (including code-pairing) - Boards (visualstudio.com) | Movilitas | Yes |  | Mariusz W | 23'08
1278824 | 1229050 | ATTP3.0 - UAE GTR production in EU (including code-pairing) - Boards (visualstudio.com) | Movilitas | Yes |  | Mariusz W | 23'08
1113913 | 1014091 | UK Legislation ME - Boards (visualstudio.com) | Movilitas | Yes | Ready for SIT | Tomasz D | 23'08
1244581 | 1244603 | UK 2.3 Deactivation Reporting Events for UK Authorities triggered for EU SKU | Movilitas | No - If agreed with Business | Required clarification -1281886 - Linked . If NO need to allign with Business that destroy scenarios shold plan after 6 months | Tomasz
| 1272480 | INC0406745- SQL error: Could not save changes of objects to database (SQL error) - Boards (visualstudio.com) |  | Yes | Incident - fixed. Requied update in ATTP by Movilitas | Tomsaz | 23 06 |  |  |  | Yes
| 1238197 | ATTP3.0 - fix for reprocessing mechanism - to retrigger PDA INC0405212 - Boards (visualstudio.com) |  | NO | Incident | Mariusz W | 23'07 |  |  | NA | NA
| 1272962 | Downtime recovery reprocessing mechanism - Long term solution - Boards (visualstudio.com) |  | Yes | Moving on may | Mariusz W | 23'05 | end of May
| 1362364 | INC0492383 - eASN that follows previous eASN triggers auto-unpacking which incorrectly triggers 3-6 message
1225694 | 1232369 | Return to ME - add GUI to set PO as REWORK |  |  | Completed
| 1114442 | Mexico ME: Stock transfer [from ME to LE area] to be done on Master Case level |  |  | Rejected - Marcin to check with Tomasz | Tomosz
Integration | TT1010383

## Entry Exit status
SIT Entry Criteria
Item​ | Criteria​ | RAG​ | Comments​
1​ | Build and FUT for all relevant systems exit has been signed off | COMPLETE
2​ | SIT scope signed off | COMPLETE
3​ | Environment availability for all relevant systems including interfaces | AMBER | OER Setup is pending SSCC label printing from TAO for manual palletization is pending
4​ | Testing collateral ready for all relevant systems | COMPLETE
5​ | Readiness of testing data for all relevant systems | COMPLETE
6​ | Test resources available and ready (roles/access) with functional knowledge | COMPLETE
7 | Test resource HPQC access with knowledge | COMPLETE
8 | SIT Kick Off Completion | COMPLETE
SIT Exit Criteria
Item​ | Criteria​ | RAG​ | Comments​ | RED
1​ | 100% of in scope end to end scripts executed |  |  | AMBER
2​ | 100% of in scope end to end scripts passed, where <100% of tests are passed, each failed or unperformed test will be the subject of discussion to enable BAT to determine if the overall test outcomes are of sufficient quality and scope to approve moving to the next phase of testing. |  |  | GREEN
3​ | All test results documented in HPQC and test execution QA completed with no outstanding observations
4​ | All defects logged in HPQC and linked with relevant test scripts
5​ | Any open defects have been documented, assigned a priority agreed with BAT technical and business stakeholders, have a planned fixed date, and agreed action/workaround plan
6​ | SIT test closure report prepared & signed off by BAT BA and STS Lead
HPQC SIT Folder:
Test Lab > 08 - GTnT > ATTP 3.0 Roadmap > Indonesia > Malmo > BO1490070 Indonesia Fixed Deployment > SIT
•Detected in cycle: Release > ATTP RoadMap > Indonesia > BO1490070 Indonesia Fixed Deployment > SIT > BO1490070 Indonesia Fixed Deployment > BO1490070 Indonesia Fixed Deployment

## Defects
Defect ID | Severity | Status | Assigned To | Assigned to Team | Defect Type | Detected By | Summary | Detected in Cycle
6983 | Medium | Open | Sudip | ITC Infotech | Authorisation | prashant_dwivedi | Error on triggering Email from FSS3 to External Email id | BO1490070 Indonesia Fixed Deployment SIT
6985 | High | Open | rishabh_chandan | ITC Infotech | Configuration | rishabh_chandan | Unable to perform Destroy All transactaion in ME HHT | BO1490070 Indonesia Fixed Deployment SIT
6989 | Medium | Open | abhishek_ash1 | ITC Infotech | Application | prashant_dwivedi | Unable to perform Destroy All transactaion in ME HHT | BO1490070 Indonesia Fixed Deployment SIT
6991 | Medium | Open | kamlakar_choudhary | ITC Infotech | Application | prashant_dwivedi | MC label printer is not working correctly | BO1490070 Indonesia Fixed Deployment SIT

## Features
CR | Features | Details | Build Owner | In Scope | Show stopper | Status /Remarks | Owner | Iteration | FUT | SIT | UAT | RT | PVT | Comments

## Test Execution Plan
Test Execution Status
Scenario ID/Name | Activity Group | Title | Testers | Local Support Required | Status | Start Date | End Date | Internal Completion Date | Feature | Remarks | Defects | SKU | Test Evidence reviewed/Approved | Remarks
ME-SIT-MD-01 | Master data | Full upload or refresh of Material Master Data from TaO ECC to Inextor through FSS3 | Prasanth |  | Passed | 2024-08-05 | 2024-08-06 | 2024-08-05 |  |  |  | 10195196, 10027458 | Not Approved | Please attach xml file with MATMAS [relevant for the tested SKU]. To be corrected now for test SKU by data team and retested; and in parallel to be followed with business for future SKUs: instead of 'GTR' in Territory characteristic, we should have 'GTR - China' or 'China - GTR' to indicate clearly GTR end market.
ME-SIT-MD-02 | Master data | Notification of Material Master Data issue following update from TaO ECC | Prasanth |  | Passed | 2024-08-05 | 2024-08-06 | 2024-08-05 |  |  |  | 10198237
ME-SIT-PO-07 | Prodution Order | Check Production Order details existing in Gate for Fixed Deployments (direct interface between TaO and FSS3) | Prasanth |  | Passed | 2024-08-05 | 2024-08-06 | 2024-08-05 |  |  |  | 10195196 | Not Approved | Please attach xml file with LOIPRO [relevant for test SKU]. BATCH ID visible in LOIPRO msg [on the screenshot], where Malang factory is non-batch managed; suggestion is to follow their process and do not push BATCH ID from TaO; for internal system needs, BATCH would be then calculated by ME T&T HH/FSS3. To be restested.
ME-SIT-PC-20 | Production change | Manual Production Change with APRISO ME T&T HH [with MC label printing only] | Kamlakar | Y | Not Completed | 2024-08-07 | 2024-08-09 | 2024-08-06 |  |  |  | 10195196 |  | ME T&T HH - different time displayed on OS window [1:51 pm] than CREATED TIME for PO Change on app [12:50 pm] – to be checked why we have that difference; and corrected [all servers and apps must be sync against the same bat time server]* METS Simulator – TBC, why in Tracking Level field we have Tracking Indicator value ‘Y’ – not a defect, but check required; BAT serialization - Outer and Master Case - wrong Factory ID used inside codes - to be corrected [FSS3 & Inextor] 2D Data Matrix on MC label - non-GS1 format; not critical for China, but spare time to be used for its correction; MC label [Evo labeler] - poor quality of 1D barcodes – to be followed with business/local team for the next phase of T&T project; printer/headers to be checked, label to be cleaned and corrected - no impact now, but critical for future production
ME-SIT-PR-14 | Production running | Production start with APRISO ME T&T HH and running in full T&T mode (with METS Simulator) | Kamlakar | Y | Passed | 2024-08-07 | 2024-08-09 | 2024-08-06 |  |  |  | 10195196
ME-SIT-RWK-18 | Manual rework | Open a previously registered Case (Open transaction on APRISO ME T&T HH) | Kamlakar | Y | Passed | 2024-08-12 | 2024-08-12 | 2024-08-07 |  |  |  | 10195196
ME-SIT-OTH-08 | Other ME | Destroy a previously registered Case in ME area (Destroy All transaction on APRISO ME T&T HH) | Kamlakar | Y | Passed | 2024-08-13 | 2024-08-13 | 2024-08-07 |  |  |  | 10195196
ME-SIT-PAL-12 | Palletization | Build a Pallet manually (Palletize transaction on APRISO ME T&T HH) | Prasanth | Y | Passed | 2024-08-14 | 2024-08-15 | 2024-08-08 |  |  |  | 10195196

## TestData
Scenario ID/Name | Test Data | Test Data Status

## Key Contacts
Name | Sno | Name | Role | Team | Email ID | OneView Id | Comment
| 1 | Anbarasu Chinnapper​​ | Project Manager​​ | ITCI | anbarasu.chinnapper@itcinfotech.com
| 2 | Aniruddha Guha​ | Deployment Lead ​​ | ITCI | Aniruddha.Guha@itcinfotech.com
| 5 | Rafael​ | Integration lead​ |  | rafael.coscolluela@syniti.com sudarshan.lakhotia@itcinfotech.com
| 6 | Ramesvar ​Giri Vasudevan​ | Test Manager​​ | ITCI | ramesvar_vasudevan2_external@bat.com
| 7 | Ajay Suresh | Master Data | ITCI | ajay.suresh@itcinfotech.com
| 8 | Parminder |  | ITCI | parminder.basanti@itcinfotech.com
| 9 | Viplav Dhandhukia​​ | Cutover Manager​​ | ITCI | Viplav.Dhandhukia@itcinfotech.com
| 10 | Viplav Dhandhukia​​ | Hypercare Manager​​ | ITCI | Viplav.Dhandhukia@itcinfotech.com
| 11 | Varun Basty Shenoy​​ | Transition Manager​​ | ITCI | varun.shenoy@itcinfotech.com
| 12 | Marcin Jatkowski​ | IT Deployment lead​​ | BAT | marcin_jatkowski@bat.com
L Team
Team

## ActionItems
Sl.No | Action item | Action Owner | RAG | Target date | Comments
1 | Test Scope Confirmation and sign off | Sandra | Completed | 2024-07-09 | Scenario can be still [potentially] modified next week(19-Jul) – after METS Simulator training. Total Scenarios in scope : 8 Total Scenarios in scope requires EM Support : 4
2 | Walkthrough on SIT Scenarios | Sandra | Completed | 2024-07-09
3 | Honeywell HHT ME - Participant ID and local ID to ITC | Anbu & Honeywell | Closed | 2024-07-12 | discussion with business, checking the feasibility to use Apriso HH (ITCI solution)
4 | Training on METS Simulator Tool Training | Sandra | Completed | 2024-07-19 | Before 19-Jul-24. Participants from ITC for Training SWAPNIL.PANSARE@itcinfotech.com Prashant.Dwivedi@itcinfotech.com Sudip.Nanda@itcinfotech.com
5 | Connectivity check between FSS3 to ATTP using sample data | Sudip & Sudarson & Veerababu | Completed | 2024-07-17 | Inprogress
6 | Connectivity check between Liz to MC level Printer using sample data | Sudip/Yogi | Completed | 7/17/2024 26-Jul-24 | Depends on SL.No. 7. Installation of Liz new panel will be completed by 16-Jul
7 | Production Reference SKU | Sandra | Completed | 2024-07-16 | 1. Chinese SKU 10195195 - Confirmed 2. • SKU No. 10198237 ROTH FF 20/200 KRE WE MAY JWLFFDP - SD37 • SKU No. 10027458 PETE RED – SD41 No Legislation. Standarad solution testing
8 | Connectivity check between Gate To Vault using sample data | Sudip | Completed | 12-Jul-24 17-Jul-24 | Depends on SL.No. 7. Ticket 77315 raised to Inexto on clarification on configuration
9 | Connectivity check between FSS3 To Gate using sample data | Sudip | Completed | 12-Jul-24 17-Jul-24 23-Jul-24 | Complete. Ticket 77315 raised to Inexto on clarification on configuration. Pending to validate product interface
10 | MWSS Setup Completion | Anbu & Honeywell | Closed | 2024-07-12 | discussion with business, checking the feasibility to use Apriso HH (ITCI solution)
11 | Demand DMND0007060 not approved : to move Integration components To test environment | Sudarshan/mary_anita_george1@bat.com | Completed | 2024-07-09
12 | HPQC Test Script Readiness | Ramesvar | Completed | 2024-07-10
13 | Execution Plan | Ramesvar | Completed | 2024-07-19
14 | Test Data Preparation | Ajay/Swapnil | Completed | 2024-07-30
15 | TAO-> ATTP and ATTP Configuration Setup | Veerababu | Completed | 2024-07-25 | Depends on SL No. 24 : CAB1 Request : CHG0198510
16 | OER Setup | Rohit | Closed | 2024-08-12 | Change request : CHG0202673 (Current Status: UAT Approved)
17 | Name of Super User responsible for SIT Execution support (Label Triggering, printing or Handheld Usage) | Local Team & Sandra | Completed | 2024-07-12 | 1. M. Luqman Habibi 2. Cholik Hari Wahyudi 3. Yaafi’ Pratama 4. Attila Shandi Prayogi Zain 5. Rayhan Bachtiar Abdillah 6. Elang Satria Perkasa
18 | Condition to SSCC label printing from TAO for manual palletization | Suprasad/Rohit | RED | 2024-08-12 | Rohit raised request RLSE0066110. As a last resort, to use virtual labels from any barcode generator to progress SIT.
19 | feasibility to use Apriso HHT Solution | Anbu & Kiran | Completed | 2024-07-12 | Sudip share the server details to sudip . 25/07- Installation done . Yogi has confirmed that they can login using test credentials
20 | Partcipant list for Training New ME HHT Solution | Sandra | Completed | 2024-07-17
21 | Training on NEW ME HHT solution to End User & Sharing Training Guide | Amitava | Completed | 2024-08-01 | Meeting Scheduled. Training Materials : https://bat.sharepoint.com/:f:/r/sites/GTnT2020/Global%20TnT%20Repository_/10%20GTnT%20Active%20Projects/30%20Other%20Initiatives/91%20BO1569818%20CR%201574234%20Replacement%20ME%20HHT%20Solution/11%20Training?csf=1&web=1&e=5D0mmE
22 | Master case template configuration with chinese characters to Inexto and Liz | Yogi | Completed | 2024-07-30 | As sandra confirmed, Use the standard template duirng SIT. If the Inexto team resolves the Chinese character issue, it will be tested in SIT
23 | DS CAB to setup this GCP in TaO and from there we need to setup the location in ATTP | Anbu & Tomasz M | Completed | 2024-07-29 | For Indonesia & Singapore GLN & GCP : DMND0008971
24 | Confirm Indonesian GCP & GLN are valid | Rohit | Completed | 2024-07-11 | CAB Request and ATTP Configuraiton request raised
25 | Additional Configuration setup for the Chinese SKU and Malaysia SKU | Suprasad / Veerababu | Completed
26 | One valid Request of MATMAS and LOIPRO for Malang | Sudip | Completed
27 | SKU Confirmaiton from MD Team | Ajay | Completed | 2024-07-30
28 | SD41 Readiness | Yogi | Completed | 2024-07-26 | Liz panel and printer is ready. Related to SL.No. 30
29 | Connectivity check and Printer configuration set up on Liz installed in office PC | Sudip/Yogi | Closed | 2024-07-29
30 | METS simulator Setup for Line system | Yogi | Completed | 2024-07-30
31 | Smoke Testing Completion | Sudip | Cm | 2024-08-02
32 | Alignment with local team for SIT test eecution in terms on any support required | Rameswar | Completed | 2024-07-31
33 | Alignment with METS team for any support during SIT execution | Rameswar/Sudip | Completed | 2024-07-31
34 | RLSE0062649 - Add Indonesia & Singapore GLN in "ZVLE_GLN_NUMBER " table in TaO - D04--->T05--->R04--->P03 system | Rohit | GREEN | 2024-08-01
35 | Alignment with EM team on 1. Whether they are clear on the test scripts that are to be executed by them. 2. Day wise alignment on execution plan 3. Alignment with METS team for support during testing of scenerio using line simulator | Rameswar | Completed | 2024-08-02
36 | ME HH - Master Data config/setup and access/users maintenance training for local technical team | Amitava | GREEN | TBC | Session to be planned later. Not part of IT readiness deployment
37 | ME HH - Remaining transaction training - separate session with all super users [business & technical] | Amitava | GREEN | TBC | Session to be planned later. Not part of IT readiness deployment
38 | Performance of production change scenario in ME HHT | Sudip/Rishab
39 | SSCC barcode not comply with the GS1 standard | SAP ECC & Rohit | RED | TBD | Incident raised. INC0930055

## Scenarios
Scenario ID | Activity group | Legislation/Market | Scenario Title | Test line required? | Malang, ID | BA | Status | Other notes for Malang, ID | Pre-requisities | Process Description | Expected Result | Component 1 | Component 2 | Component 3 | Component 4 | Component 5 | Component 6 | Component 7 | Component 8 | Component 9 | Component 10 | Component 11 | Component 12 | Component 13 | Component 14 | Component 15
ME-SIT-MD-01 | Master data | GENERIC | Full upload or refresh of Material Master Data from TaO ECC to Inextor through FSS3 | N | X | Sandra | Completed | -Elective, Pack level tracking SKU -FMC [Cigarettes material group] -End Market - China and domestic/Malaysian, produced in Malang, ID -Standard Material Master iDOC to be tested E2E | Data: 1 Elective or Legal SKU with correct T&T characteristics setting Process: N/A Systems: TaO: 1 Elective or Legal SKU with correct T&T characteristics setting FSS3: Scheduled job dedicated for MD sending to Inextor Gate is enabled | Material Master Data is sent from TaO ECC to Inextor Gate through FSS3. SKU is valid and Manufactured Product is ready for future production run | Specific Material number is visible in SKU tab in Inextor Gate and data is marked as synchronized with Inextor Vault(s). Same SKU number can be found in Manufactured Product tab in Inextor Gate. | ME_MD_MD-UPLOAD-MODIF_DEF
ME-SIT-MD-02 | Master data | GENERIC | Notification of Material Master Data issue following update from TaO ECC | N | X | Sandra | Completed | -SKU with missing T&T characteristic like Tracking Indicator -FMC [Cigarettes material group] -End Market - China and domestic/Malaysian, produced in Malang, ID -Standard scheduled job to be tested E2E - notification sending to defined list of recipients | Data: 1 Elective or Legal SKU with missing T&T characteristic value (like Tracking Indicator) Process: N/A Systems: TaO: 1 Elective or Legal SKU with missing T&T characteristic value (like Tracking Indicator) FSS3: Scheduled job dedicated for MD issue alert sending is enabled and MD SU is registered as recipient | SKU update (after its modification in TaO) is sent to T&T systems, however Material does not reach Inextor Gate due to missing T&T characteristic value and Master Data Super User is alerted via emial in order to allow the issue to be fixed and prevent a production change from being carried out | Email notification sent to the defined recipient(s) with information regarding invalid SKU | ME_MD_MD-ISSUE-NOTIF-EXTENDED_NEG
ME-SIT-PO-07 | Prodution Order | GENERIC | Check Production Order details existing in Gate for Fixed Deployments (direct interface between TaO and FSS3) | N | X | Sandra | Completed | -Elective, Pack level tracking SKU -Production Order created in TaO per standard for Cigarettes [quantity in TH] -FMC [Cigarettes material group] -End Market - China and domestic/Malaysian, produced in Malang, ID -Standard Production Order iDOC to be tested E2E | Data: 1 Elective SKU with correct T&T characteristics setting [Pack Level Tracking] 1 Production Order created in TaO ECC with 'next day' execution date Process: Material Master data sent successfully to FSS3 & Gate in advance [before Production Order details] Systems: TaO: 1 Elective SKU with correct T&T characteristics setting [Pack Level Tracking]; 1 PO created for the dedicated SKU FSS3: Scheduled job dedicated for PO details sending to Inextor Gate is enabled | Production Order details are sent from TaO ECC to Inextor Gate through FSS3. | Specific Production Order number and details are visible in Production Orders tab in Inextor Gate and data is marked as synchronized with Inextor Vault(s). | ME_PR_PO-SEND-TAO_FD
ME-SIT-PC-20 | Production change | ID | Manual Production Change with APRISO ME T&T HH [with MC label printing only] | Y [only MC labeller is needed] | X | Sandra | Completed | -Elective, Pack level tracking SKU -FMC [Cigarettes material group] -End Market - China and domestic/Malaysian, produced in Malang, ID -Standard communication with FSS3, METS, Inextor and MC printer to be tested -at least 1 MC label to be printed -for the above action, local SU support is required | Data: 1 Elective SKU with Pack Level Tracking indicator for product which requires only MC label generation with Inextor solution [PK and OUT labels are printed offline]; Production Order in TaO with status Released; Process: N/A Systems: TaO ECC: 1 Production Order with status Released; APRISO ME T&T HH: Apriso app and communication with FSS3 is enabled; FSS3: Communication is established with Inextor Gate and METS Simulator for the specific production line; Inextor Gate: Prepared SKU visible in Manufactured Product tab and PO visible in Production Order tab; MC printing templates and layouts setup; Communication is established with LIZ PC Panel for the specific production line; MC Label Printer is available and ready for printing; | Standard PO Change operation for product which requires only MC label generation with Inextor solution; | Success message is displayed on ME T&T HH screen. New Production Order is started on the METS Simulator; PO details are visibile on LIZ PC Panel. First batch of UIDs is sent to MC Label printer. At least 1 MC Label printed sucessfully. | ME_PR_PO-CHANGE-APRISO-HH_ID
ME-SIT-PR-14 | Production running | ID | Production start with APRISO ME T&T HH and running in full T&T mode (with METS Simulator) | Y/N [MC labeller is needed] | X | Sandra | In Progress | ! scenario to be improved after METS Simualtor training ! -Elective, Pack level tracking SKU -FMC [Cigarettes material group] -End Market - China and domestic/Malaysian, produced in Malang, ID -Standard communication with FSS3, ATTp, METS, -at least XX number of MCs to be produced [== one full Pallet quantity] -TBC is local SU support is required fro METS Simualtor | Data: 1 Elective SKU with Pack Level Tracking indicator; 1 Production Order in TaO with status Released; Process: N/A Systems: TaO ECC: 1 Production Order with status Released; APRISO ME T&T HH: Apriso app and communication with FSS3 is enabled; FSS3: Communication is established with Inextor Gate and METS Simulator for the specific production line; Inextor Gate: Communication is established with LIZ PC Panel for the specific production line; MC Label printer is available and ready for codes application; | Production Order start with PO Change transaction on APRISO ME T&T HH and successfull production run in full T&T mode with METS Simulator tool. As result, Master Case aggregations are reported to local FSS3 and from there to ATTp repository. | New Master Case aggregations are created on the line. Their hierarchies are reported successfully to FSS3 by METS Simulator and from there to ATTp repository. | ME_PR_PO-CHANGE-APRISO-HH_DEF | ME_PR_PO-RUN-METS-SIM_DEF
ME-SIT-RWK-18 | Manual rework | GENERIC | Open a previously registered Case (Open transaction on APRISO ME T&T HH) | N | X | Sandra | Completed | -Elective, Pack level tracking SKU -FMC [Cigarettes material group] -End Market - China and domestic/Malaysian, produced in Malang, ID -Standard communication with FSS3, ATTp to be tested -containers [full MC] to be produced with METS Simulator, but barcodes for scanning with real HH device must be printed on a paper -for the above action, local SU support is required | Data: 1 Elective or Legal SKU with Pack Level Tracking indicator; 1 PO for the chosen SKU in TaO and T&T; Process: Master Case produced on T&T production line (not GRed yet) for which it was decided that rework is required Systems: FSS3: Master Case created on the line for T&T SKU and reported successfully to FSS3 by Line System APRISO ME T&T HH/Scanner: Device available and communication with FSS3 application is established ATTP: Aggregations for the created Master Cases for T&T SKU recored and reported successfully | Master Case hieararchy disaggregated via Open transaction on APRISO ME T&T HH. MC destroyed.Unapcking reported to ATTp. | Old Master Case disaggregation recorded in ATTp. | ME_RW_OPEN-APRISO-HH_DEF | ME_RW_INSPECT-APRISO-HH-MC_DECOM | ME_RW_OPEN-ATTP_DEF
ME-SIT-OTH-08 | Other ME | GENERIC | Destroy a previously registered Case in ME area (Destroy All transaction on APRISO ME T&T HH) | N | X | Sandra | Completed | -Elective, Pack level tracking SKU -FMC [Cigarettes material group] -End Market - China and domestic/Malaysian, produced in Malang, ID -Standard communication with FSS3, ATTp to be tested -containers [full MC] to be produced with METS Simulator, but barcodes for scanning with real HH device must be printed on a paper -for the above action, local SU support is required | Data: 1 Elective or Legal SKU with Pack Level Tracking indicator; Process: Master Case produced on T&T production line - product quality issue noticed and decision made for the whole product destruction; Systems: FSS3: Master Case created on the line for T&T SKU and reported successfully to FSS3 by Line System APRISO ME T&T HH: Device available and communication with FSS3 application is established ATTP: Aggregation for the created Master Case for T&T SKU recored and reported successfully to Authorities [if required] | Due to quality (or any other) issues, Master Case produced in ME area (but not GRed yet) is fully decommissioned with Destroy All transaction on APRISO ME T&T HH and then physically destroyed (including Packs). PK & OUT & MC IDs must not be used in any other aggregation. | Destroy event for MC and its children is reported successfully to ATTp | ME_DESTRU_DESTROYALL-APRISO-HH_DEF | ME_DESTRU_DESTROYALL-ATTP_DEF
ME-SIT-PAL-12 | Palletization | GENERIC | Build a Pallet manually (Palletize transaction on APRISO ME T&T HH) | N | X | Sandra | Completed | -Elective, Pack level tracking SKU -FMC [Cigarettes material group] -End Market - China and domestic/Malaysian, produced in Malang, ID -Standard communication with FSS3, ATTp to be tested -containers [XX full MCs] to be produced with METS Simulator, but barcodes for scanning with real HH device must be printed on a paper -new SSCC label must be pre-printed -for the above action, local SU support is require | Data: 1 Elective or Legal SKU with Pack Level Tracking indicator; 1 Production Order in TaO; Process: Relevant number of Master Cases produced on T&T production line - quantity depends on UAT preparation agreement - if it will be number of a full standard Pallet or smaller for local team convenience; Systems: FSS3: Master Cases created on the line for T&T SKU and reported successfully to FSS3 by Line System APRISO ME T&T HH/Scanner: Device available and communication with FSS3 application is established ATTP: Aggregations for the created Master Cases for T&T SKU recored and reported successfully | Pallet built manually with APRISO ME T&T HH; as result Pallet Aggregation message is reported to FSS3 and then after successfull validation, Pallet Aggregation is reported to ATTp. | Success message displayed on APRISO ME T&T HH. Pallet aggregation recorded in ATTp. | ME_PAL_PAL-BUILD-APRISO-HH_MANUAL | ME_PAL_PAL-BUILD-ATTP_DEF

## Smoke Testing
S.No. |  | Criteria | RAG | Comments
1 | ME | ECC to FSS MATMAS for 196 SKU(ECC and FSS screenshot) | Completed
2 | ME | ECC to FSS New LOIPRO for 196 SKU(ECC and FSS screenshot) | Completed
3 | ME | FSS to GATE SKU transfer (Gate screenshot) | Completed
4 | ME | FSS to GATE PO transfer (Gate screenshot) | Completed
5 | ME | Generate MC and pallet hierarchy send to ATTP(FSS and attp screenshot) | Completed
6 | ME | PO change process in FSS(Auto PO start in LIZ, Line system) | Completed
7 | ME | Printer label printing screenshot | Completed | Using Sample template
8 | ME | Place holder for ME HHT smoke test - PO change | Completed
9 | ATTP | Validate created MC and pallet in ATTP | Completed | Depend on SL. No. 5
10 | OER | Check OER reporting except for China SKU

## Scenarios_Steps
Scenario ID | Activity group | Legislation/Market | Scenario Title | Test line required? | Malang, ID | Other notes for Malang, ID | Pre-requisities | Process Description | Expected Result | Component Name | Component Description | Step | Step description | Expected Result | Assigned To | Resource Name | Execution Status
ME-SIT-MD-01 | Master data | GENERIC | Full upload or refresh of Material Master Data from TaO ECC to Inextor through FSS3 | N | X | -Elective, Pack level tracking SKU -FMC [Cigarettes material group] -End Market - China and domestic/Malaysian, produced in Malang, ID -Standard Material Master iDOC to be tested E2E | Data: 1 Elective or Legal SKU with correct T&T characteristics setting Process: N/A Systems: TaO: 1 Elective or Legal SKU with correct T&T characteristics setting FSS3: Scheduled job dedicated for MD sending to Inextor Gate is enabled | Material Master Data is sent from TaO ECC to Inextor Gate through FSS3. SKU is valid and Manufactured Product is ready for future production run | Specific Material number is visible in SKU tab in Inextor Gate and data is marked as synchronized with Inextor Vault(s). Same SKU number can be found in Manufactured Product tab in Inextor Gate. | ME_MD_MD-UPLOAD-MODIF_DEF | Full upload or refresh of Material Master Data from TaO ECC to Inextor | Step 1 | TaO ECC: Run BD10 transaction to create new MATMAS Idoc for prepared SKU | Material Master Data Idoc created successfully - confirmation displayed | ITC | Prasanth | Pass
[10 empty] | ME_MD_MD-UPLOAD-MODIF_DEF | Full upload or refresh of Material Master Data from TaO ECC to Inextor | Step 2 | TaO ECC: [Optional - depends if SU has access to it; not mandatory] Go to WE14 and trigger Idoc generated in Step 1 to FSS3 | Prepared Idoc processed by system and sent to FSS | ITC | Prasanth | Pass
[10 empty] | ME_MD_MD-UPLOAD-MODIF_DEF | Full upload or refresh of Material Master Data from TaO ECC to Inextor | Step 3 | TaO ECC: [Optional - depends if SU has access to it; not mandatory] Run WE02 transcation and check if MATMAS message (Idoc) has been sent correctly from TaO | MATMAS Idoc marked as sent successfully - Current status field with value 03 | ITC | Prasanth | Pass
[10 empty] | ME_MD_MD-UPLOAD-MODIF_DEF | Full upload or refresh of Material Master Data from TaO ECC to Inextor | Step 4 | [OPTIONAL - can be skipped if there is no T&T IT Super User] FSS3: Check if received SKU has status VALID | Material number has status VALID, no errors registered | ITC | Prasanth | Pass
[10 empty] | ME_MD_MD-UPLOAD-MODIF_DEF | Full upload or refresh of Material Master Data from TaO ECC to Inextor | Step 5 | GATE APP: Check if triggered SKU is recorded correctly in SKU tab and Manufactured Product is created accordingly | SKU was successfully sent to Inextor GATE and Manufactured Product was created accordingly. Data is ready for future production running | ITC | Prasanth | Pass
ME-SIT-MD-02 | Master data | GENERIC | Notification of Material Master Data issue following update from TaO ECC | N | X | -SKU with missing T&T characteristic like Tracking Indicator -FMC [Cigarettes material group] -End Market - China and domestic/Malaysian, produced in Malang, ID -Standard scheduled job to be tested E2E - notification sending to defined list of recipients | Data: 1 Elective or Legal SKU with missing T&T characteristic value (like Tracking Indicator) Process: N/A Systems: TaO: 1 Elective or Legal SKU with missing T&T characteristic value (like Tracking Indicator) FSS3: Scheduled job dedicated for MD issue alert sending is enabled and MD SU is registered as recipient | SKU update (after its modification in TaO) is sent to T&T systems, however Material does not reach Inextor Gate due to missing T&T characteristic value and Master Data Super User is alerted via emial in order to allow the issue to be fixed and prevent a production change from being carried out | Email notification sent to the defined recipient(s) with information regarding invalid SKU | ME_MD_MD-ISSUE-NOTIF-EXTENDED_NEG | Notification of Material Master Data issue following update from TaO ECC [extended version] | Step 1 | TaO ECC: Run BD10 transaction to create new MATMAS Idoc for prepared SKU (with missing T&T characteristic value (like Tracking Indicator)) | Material Master Data Idoc created successfully - confirmation displayed | ITC | Prasanth | Pass
[10 empty] | ME_MD_MD-ISSUE-NOTIF-EXTENDED_NEG | Notification of Material Master Data issue following update from TaO ECC [extended version] | Step 2 | TaO ECC: [Optional - depends if SU has access to it; not mandatory] Go to WE14 and trigger Idoc generated in Step 1 to FSS3 | Prepared Idoc processed by system and sent to FSS | ITC | Prasanth | Pass
[10 empty] | ME_MD_MD-ISSUE-NOTIF-EXTENDED_NEG | Notification of Material Master Data issue following update from TaO ECC [extended version] | Step 3 | TaO ECC: [Optional - depends if SU has access to it; not mandatory] Run WE02 transcation and check if MATMAS message (Idoc) has been sent correctly from TaO | MATMAS Idoc marked as sent successfully - Current status field with value 03 | ITC | Prasanth | Pass
[10 empty] | ME_MD_MD-ISSUE-NOTIF-EXTENDED_NEG | Notification of Material Master Data issue following update from TaO ECC [extended version] | Step 4 | Outlook: Check if email [with a list of problematic SKUs] has reached your Inbox (and/or other recipients defined in FSS3 as Super Users). Confirm that below data is displayed in the notification message: - MATERIAL NUMBER - WARNING/ERROR MESSAGE - PLANT CODE - MATERIAL DESCRIPTION. Take a screenshot. | Email notification received and INVALID Material Number[s] is[are] included in the list. There is clear indication regarding: - MATERIAL NUMBER - WARNING/ERROR MESSAGE - PLANT CODE - MATERIAL DESCRIPTION. | ITC | Prasanth | Fail
ME-SIT-PO-07 | Prodution Order | GENERIC | Check Production Order details existing in Gate for Fixed Deployments (direct interface between TaO and FSS3) | N | X | -Elective, Pack level tracking SKU -Production Order created in TaO per standard for Cigarettes [quantity in TH] -FMC [Cigarettes material group] -End Market - China and domestic/Malaysian, produced in Malang, ID -Standard Production Order iDOC to be tested E2E | Data: 1 Elective SKU with correct T&T characteristics setting [Pack Level Tracking] 1 Production Order created in TaO ECC with 'next day' execution date Process: Material Master data sent successfully to FSS3 & Gate in advance [before Production Order details] Systems: TaO: 1 Elective SKU with correct T&T characteristics setting [Pack Level Tracking]; 1 PO created for the dedicated SKU FSS3: Scheduled job dedicated for PO details sending to Inextor Gate is enabled | Production Order details are sent from TaO ECC to Inextor Gate through FSS3. | Specific Production Order number and details are visible in Production Orders tab in Inextor Gate and data is marked as synchronized with Inextor Vault(s). | ME_PR_PO-SEND-TAO_FD | Production Order details sending from TaO to FSS3 for T&T product (PK level tracking) - Fixed Deployment [no T&T legislation] | Step 1 | TaO ECC: [OPTIONAL if SU wish to expedite process and do not wait for automatic Production Order arrival from TaO to FSS3] Login into system as Scheduler Super User | Successfull SAP login | ITC | Prasanth | Pass
[10 empty] | ME_PR_PO-SEND-TAO_FD | Production Order details sending from TaO to FSS3 for T&T product (PK level tracking) - Fixed Deployment [no T&T legislation] | Step 2 | TaO ECC: [OPTIONAL if SU wish to expedite process and do not wait for automatic Production Order arrival from TaO to FSS3] Go to ZMME_SENDPRODORD transaction and fill relevant values into Plant, Order, Material, Planning Plant fields and execute it | Transaction executed successfully, no errors displayed, only 'OK' indication | ITC | Prasanth | Pass
[10 empty] | ME_PR_PO-SEND-TAO_FD | Production Order details sending from TaO to FSS3 for T&T product (PK level tracking) - Fixed Deployment [no T&T legislation] | Step 3 | FSS3 APP: [OPTIONAL - depends on IT SU availability] Wait 5-10 mins and then login FSS3 APP server as amdinistrator and then login Apriso Desktop Client with relevant credentials | Successfull FSS3 server and Apriso Desktop Client login | ITC | Prasanth | Pass
[10 empty] | ME_PR_PO-SEND-TAO_FD | Production Order details sending from TaO to FSS3 for T&T product (PK level tracking) - Fixed Deployment [no T&T legislation] | Step 4 | FSS3 APP: [OPTIONAL - depends on IT SU availability] Go to Immediate Job History list | List displayed correctly, at least 1 message visible | ITC | Prasanth | Pass
[10 empty] | ME_PR_PO-SEND-TAO_FD | Production Order details sending from TaO to FSS3 for T&T product (PK level tracking) - Fixed Deployment [no T&T legislation] | Step 5 | FSS3 APP: [OPTIONAL - depends on IT SU availability] Find the triggered Production Order details message (LOIPRO iDOC) by filtering messages, for example with PO number | LOIPRO message found successfully on the list | ITC | Prasanth | Pass
[10 empty] | ME_PR_PO-SEND-TAO_FD | Production Order details sending from TaO to FSS3 for T&T product (PK level tracking) - Fixed Deployment [no T&T legislation] | Step 6 | FSS3 APP: [OPTIONAL - depends on IT SU availability] Confirm that that specific message was processed successfully by Apriso (status Success) | XML was processed by Apriso without issues | ITC | Prasanth | Pass
[10 empty] | ME_PR_PO-SEND-TAO_FD | Production Order details sending from TaO to FSS3 for T&T product (PK level tracking) - Fixed Deployment [no T&T legislation] | Step 7 | FSS3 APP: [OPTIONAL - depends on IT SU availability] If yes, then go to the message details and content, check with Scheduler/SU if PO details are correct | Scheduler/SU confirmed that PO details are correct and expected based on PO preparation in TaO ECC | ITC | Prasanth | Pass
[10 empty] | ME_PR_PO-SEND-TAO_FD | Production Order details sending from TaO to FSS3 for T&T product (PK level tracking) - Fixed Deployment [no T&T legislation] | Step 8 | GATE APP: Login Gate application | Successfull Gate application login, menu visible | ITC | Prasanth | Pass
[10 empty] | ME_PR_PO-SEND-TAO_FD | Production Order details sending from TaO to FSS3 for T&T product (PK level tracking) - Fixed Deployment [no T&T legislation] | Step 9 | GATE APP: Go to Production -> Production Orders tab and find there triggered PO by filtering list | Triggered Production Order found on the list | ITC | Prasanth | Pass
[10 empty] | ME_PR_PO-SEND-TAO_FD | Production Order details sending from TaO to FSS3 for T&T product (PK level tracking) - Fixed Deployment [no T&T legislation] | Step 10 | GATE APP: Double click on the Production Order number found in the previous step | Detailed view window opened for the chosen PO | ITC | Prasanth | Pass
[10 empty] | ME_PR_PO-SEND-TAO_FD | Production Order details sending from TaO to FSS3 for T&T product (PK level tracking) - Fixed Deployment [no T&T legislation] | Step 11 | GATE APP: Check if found PO has relevant values in SKU, Quantity and Line ID fields. Have a look as well on Expected date | Values are correct and expected based on Production Order prepared in TaO ECC | ITC | Prasanth | Pass
ME-SIT-PC-20 | Production change | ID | Manual Production Change with APRISO ME T&T HH [with MC label printing only] | Y [only MC labeller is needed] | X | -Elective, Pack level tracking SKU -FMC [Cigarettes material group] -End Market - China and domestic/Malaysian, produced in Malang, ID -Standard communication with FSS3, METS, Inextor and MC printer to be tested -at least 1 MC label to be printed -for the above action, local SU support is required | Data: 1 Elective SKU with Pack Level Tracking indicator for product which requires only MC label generation with Inextor solution [PK and OUT labels are printed offline]; Production Order in TaO with status Released; Process: N/A Systems: TaO ECC: 1 Production Order with status Released; APRISO ME T&T HH: Apriso app and communication with FSS3 is enabled; FSS3: Communication is established with Inextor Gate and METS Simulator for the specific production line; Inextor Gate: Prepared SKU visible in Manufactured Product tab and PO visible in Production Order tab; MC printing templates and layouts setup; Communication is established with LIZ PC Panel for the specific production line; MC Label Printer is available and ready for printing; | Standard PO Change operation for product which requires only MC label generation with Inextor solution; | Success message is displayed on ME T&T HH screen. New Production Order is started on the METS Simulator; PO details are visibile on LIZ PC Panel. First batch of UIDs is sent to MC Label printer. At least 1 MC Label printed sucessfully. | ME_PR_PO-CHANGE-APRISO-HH_ID | Manual Production Change with APRISO ME T&T HH for product which requires only MC label generation with Inextor solution; | Step 1 | ME-HH: Login Apriso application and check if PO Change transaction is visible in the main menu | Successfull ME HH login and PO Change transaction is available for usage | EM |  | Pass
[10 empty] | ME_PR_PO-CHANGE-APRISO-HH_ID | Manual Production Change with APRISO ME T&T HH for product which requires only MC label generation with Inextor solution; | Step 2 | ME-HH: Run PO Change transaction | PO Change run successfully | EM |  | Pass
[10 empty] | ME_PR_PO-CHANGE-APRISO-HH_ID | Manual Production Change with APRISO ME T&T HH for product which requires only MC label generation with Inextor solution; | Step 3 | ME-HH: Select relevant Production Line number from the list | Line confirmed, list of released POs displayed | EM |  | Pass
[10 empty] | ME_PR_PO-CHANGE-APRISO-HH_ID | Manual Production Change with APRISO ME T&T HH for product which requires only MC label generation with Inextor solution; | Step 4 | ME-HH: Select PO number from the list. Confirm that correct Production Order details are displayed in Production Change form - check PO number, SKU, Line ID and Batch [if required in your site] | All required data for Production Order change is available | EM |  | Pass
[10 empty] | ME_PR_PO-CHANGE-APRISO-HH_ID | Manual Production Change with APRISO ME T&T HH for product which requires only MC label generation with Inextor solution; | Step 5 | ME-HH: Select 'Change' Request Type value'. Next, click the right arrow to confirm form and start new Production Order | Form was subbmitted and application is processing the data | EM |  | Pass
[10 empty] | ME_PR_PO-CHANGE-APRISO-HH_ID | Manual Production Change with APRISO ME T&T HH for product which requires only MC label generation with Inextor solution; | Step 6 | ME-HH: Confirm that successfull response is displayed on the HH screen | Success message displayed on ME HH screen | EM |  | Pass
[10 empty] | ME_PR_PO-CHANGE-APRISO-HH_ID | Manual Production Change with APRISO ME T&T HH for product which requires only MC label generation with Inextor solution; | Step 7 | METS Operator Panel: Check if relevant PO details (dispalyed on ME T&T HH in Step 4) are visible on METS side. If OK, click Aknowledge button to upload the data | All PO details, from the Step 4, are visible on METS Panel. Acknowledged and data uploaded | EM |  | Pass
[10 empty] | ME_PR_PO-CHANGE-APRISO-HH_ID | Manual Production Change with APRISO ME T&T HH for product which requires only MC label generation with Inextor solution; | Step 8 | LIZ Panel: Confirm that relevant PO details (dispalyed on ME T&T HH in Step 4) are visible on the LIZ screen and 1st batch of codes was pushed to MC Label printer | All PO details from the Step 4 are visible on LIZ Panel and batch of UIDs was generated, pushed to MC Printer | ITC | Kamlakar | Pass
[10 empty] | ME_PR_PO-CHANGE-APRISO-HH_ID | Manual Production Change with APRISO ME T&T HH for product which requires only MC label generation with Inextor solution; | Step 9 | MC Labeller: Trigger manually printing to verify physical label and its content | MC Label printed. Content correct and relevant for the used printing template | EM |  | Pending for Execution
ME-SIT-PR-14 | Production running | ID | Production start with APRISO ME T&T HH and running in full T&T mode (with METS Simulator) | Y/N [MC labeller is needed] | X | ! scenario to be improved after METS Simualtor training ! -Elective, Pack level tracking SKU -FMC [Cigarettes material group] -End Market - China and domestic/Malaysian, produced in Malang, ID -Standard communication with FSS3, ATTp, METS, -at least XX number of MCs to be produced [== one full Pallet quantity] -TBC is local SU support is required fro METS Simualtor | Data: 1 Elective SKU with Pack Level Tracking indicator; 1 Production Order in TaO with status Released; Process: N/A Systems: TaO ECC: 1 Production Order with status Released; APRISO ME T&T HH: Apriso app and communication with FSS3 is enabled; FSS3: Communication is established with Inextor Gate and METS Simulator for the specific production line; Inextor Gate: Communication is established with LIZ PC Panel for the specific production line; MC Label printer is available and ready for codes application; | Production Order start with PO Change transaction on APRISO ME T&T HH and successfull production run in full T&T mode with METS Simulator tool. As result, Master Case aggregations are reported to local FSS3 and from there to ATTp repository. | New Master Case aggregations are created on the line. Their hierarchies are reported successfully to FSS3 by METS Simulator and from there to ATTp repository. | ME_PR_PO-CHANGE-APRISO-HH_DEF | Manual Production Change with APRISO ME T&T HH | Step 1 | ME-HH: Login Apriso application and check if PO Change transaction is visible in the main menu | Successfull ME HH login and PO Change transaction is available for usage | EM |  | Pass
[10 empty] | ME_PR_PO-CHANGE-APRISO-HH_DEF | Manual Production Change with APRISO ME T&T HH | Step 2 | ME-HH: Run PO Change transaction | PO Change run successfully | EM |  | Pass
[10 empty] | ME_PR_PO-CHANGE-APRISO-HH_DEF | Manual Production Change with APRISO ME T&T HH | Step 3 | ME-HH: Select relevant Production Line number from the list | Line confirmed, list of released POs displayed | EM |  | Pass
[10 empty] | ME_PR_PO-CHANGE-APRISO-HH_DEF | Manual Production Change with APRISO ME T&T HH | Step 4 | ME-HH: Select PO number from the list. Confirm that correct Production Order details are displayed in Production Change form - check PO number, SKU, Line ID and Batch [if required in your site] | All required data for Production Order change is available | EM |  | Pass
[10 empty] | ME_PR_PO-CHANGE-APRISO-HH_DEF | Manual Production Change with APRISO ME T&T HH | Step 5 | ME-HH: Select 'Change' Request Type value'. Next, click the right arrow to confirm form and start new Production Order | Form was subbmitted and application is processing the data | EM |  | Pass
[10 empty] | ME_PR_PO-CHANGE-APRISO-HH_DEF | Manual Production Change with APRISO ME T&T HH | Step 6 | ME-HH: Confirm that successfull response is displayed on the HH screen | Success message displayed on ME HH screen | EM |  | Pass
[10 empty] | ME_PR_PO-CHANGE-APRISO-HH_DEF | Manual Production Change with APRISO ME T&T HH | Step 7 | METS Operator Panel: Check if relevant PO details (dispalyed on ME T&T HH in Step 4) are visible on METS side. If OK, click Aknowledge button to upload the data | All PO details, from the Step 4, are visible on METS Panel. Acknowledged and data uploaded | EM |  | Pass
[10 empty] | ME_PR_PO-CHANGE-APRISO-HH_DEF | Manual Production Change with APRISO ME T&T HH | Step 8 | LIZ Panel: Confirm that relevant PO details (dispalyed on ME T&T HH in Step 4) are visible on the LIZ screen and codes were pushed to printers | All PO details from the Step 4 are visible on LIZ Panel and UIDs was generated, pushed to printers | ITC | Kamlakar | Pass
[10 empty] | ME_PR_PO-RUN-METS-SIM_DEF | Production running in full T&T mode with METS Simulator tool | Step 1 | METS Simulator tool: Start T&T production simulation with the METS Simulator tool | Simualtion has been started. First MC hierarchy message triggered from the METS Simualtor tool | EM
[10 empty] | ME_PR_PO-RUN-METS-SIM_DEF | Production running in full T&T mode with METS Simulator tool | Step 2 | FSS3 APP: Login into Apriso Desktop Client and check if Case Hierarchy Message was received from METS by FSS3. | CHM received successfully | ITC | Kamlakar
[10 empty] | ME_PR_PO-RUN-METS-SIM_DEF | Production running in full T&T mode with METS Simulator tool | Step 3 | FSS3 DB: Login into FSS3 DB and find MC ID for which CHM was received in the Step 2. Confirm that its status is VERIFIED and all production details are visible | Master Case saved in FSS3 DB with VERIFIED status | ITC | Kamlakar
[10 empty] | ME_PR_PO-RUN-METS-SIM_DEF | Production running in full T&T mode with METS Simulator tool | Step 4 | FSS3 DB: Confirm that Commissioning & Packing events were triggered to ATTp for that Master Case | Message triggered to ATTp | ITC | Kamlakar
[10 empty] | ME_PR_PO-RUN-METS-SIM_DEF | Production running in full T&T mode with METS Simulator tool | Step 5 | ATTp: Login ATTp platform and go to Serialized containers/items transaction/view | Successfull login to ATTp, no issues with access to Serialized containers/items | ITC | Kamlakar
[10 empty] | ME_PR_PO-RUN-METS-SIM_DEF | Production running in full T&T mode with METS Simulator tool | Step 6 | ATTp: Find Master Case registered from the Step 2 by filling filters with MC's Serial Number and your Plant Number, and then click 'Run'/'Execute' | Registered MC is found successfully in ATTp and its production details are displayed on the screen | ITC | Kamlakar
[10 empty] | ME_PR_PO-RUN-METS-SIM_DEF | Production running in full T&T mode with METS Simulator tool | Step 7 | ATTp: Go to event view and confirm that Commissioning and Packing events are registered for the Master Case | Commissioning and Packing events are visible on the event list. Date and time for events are valid | ITC | Kamlakar
[10 empty] | ME_PR_PO-RUN-METS-SIM_DEF | Production running in full T&T mode with METS Simulator tool | Step 8 | ATTp: Go to hierarchy view for the Master Case and confirm that Outers and Packs are visible in the hierarchy list | Containers list displayed | ITC | Kamlakar
[10 empty] | ME_PR_PO-RUN-METS-SIM_DEF | Production running in full T&T mode with METS Simulator tool | Step 9 | ATTp: Choose one Pack ID from the list, click on it and confirm that Commissioning event was registered | Commissioning event visible on the list | ITC | Kamlakar
ME-SIT-RWK-18 | Manual rework | GENERIC | Open a previously registered Case (Open transaction on APRISO ME T&T HH) | N | X | -Elective, Pack level tracking SKU -FMC [Cigarettes material group] -End Market - China and domestic/Malaysian, produced in Malang, ID -Standard communication with FSS3, ATTp to be tested -containers [full MC] to be produced with METS Simulator, but barcodes for scanning with real HH device must be printed on a paper -for the above action, local SU support is required | Data: 1 Elective or Legal SKU with Pack Level Tracking indicator; 1 PO for the chosen SKU in TaO and T&T; Process: Master Case produced on T&T production line (not GRed yet) for which it was decided that rework is required Systems: FSS3: Master Case created on the line for T&T SKU and reported successfully to FSS3 by Line System APRISO ME T&T HH/Scanner: Device available and communication with FSS3 application is established ATTP: Aggregations for the created Master Cases for T&T SKU recored and reported successfully | Master Case hieararchy disaggregated via Open transaction on APRISO ME T&T HH. MC destroyed.Unapcking reported to ATTp. | Old Master Case disaggregation recorded in ATTp. | ME_RW_OPEN-APRISO-HH_DEF | Open a previously registered Master Case with ME T&T HH [Open Transaction] | Step 1 | ME-HH: Login Apriso application and check if Open transaction is visible in main menu | Successfull ME HH login and Open transaction is available for usage | EM
[10 empty] | ME_RW_OPEN-APRISO-HH_DEF | Open a previously registered Master Case with ME T&T HH [Open Transaction] | Step 2 | ME-HH: Run Open transaction and scan Master Case label | Open transaction launched and Master Case ID accepted | EM
[10 empty] | ME_RW_OPEN-APRISO-HH_DEF | Open a previously registered Master Case with ME T&T HH [Open Transaction] | Step 3 | ME-HH: Click the right arrow button to confirm operation. As result MC will be disaggregated and its ID will be decommissioned | Operation completed successfully, no error displayed | EM
[10 empty] | ME_RW_INSPECT-APRISO-HH-MC_DECOM | Inspect a registered DECOMMISSIONED Master Case [Inspect transaction on APRISO ME T&T HH] | Step 1 | ME-HH: Login Apriso application and check if Inspect transaction is visible in main menu | Successfull ME HH login and Inspect transaction is available for usage | EM
[10 empty] | ME_RW_INSPECT-APRISO-HH-MC_DECOM | Inspect a registered DECOMMISSIONED Master Case [Inspect transaction on APRISO ME T&T HH] | Step 2 | ME-HH: Run Inspect transcation and scan a Master Case label (impacted by the last operation) | Inspect transcation run and Master Case label scanned correctly | EM
[10 empty] | ME_RW_INSPECT-APRISO-HH-MC_DECOM | Inspect a registered DECOMMISSIONED Master Case [Inspect transaction on APRISO ME T&T HH] | Step 3 | ME-HH: Check if displayed status for the scanned container is DECOMMISSIONED | Status DECOMMISSIONED is confirmed | EM
[10 empty] | ME_RW_INSPECT-APRISO-HH-MC_DECOM | Inspect a registered DECOMMISSIONED Master Case [Inspect transaction on APRISO ME T&T HH] | Step 4 | ME-HH: Check Number of children field and confirm that value is '0' | Number of children field equals '0' | EM
[10 empty] | ME_RW_OPEN-ATTP_DEF | Confirm reporting results in ATTp for opened Master Case | Step 1 | ATTp: Login ATTp platform and go to Serialized containers/items transaction/view | Successfull login to ATTp, no issues with access to Serialized containers/items | ITC | Kamlakar
[10 empty] | ME_RW_OPEN-ATTP_DEF | Confirm reporting results in ATTp for opened Master Case | Step 2 | ATTp: Find the opened Master Case by filling filters with MC's Serial Number and Plant Number, and then click 'Run'/'Execute' | Registered MC is found successfully in ATTp and its production details are displayed on the screen | ITC | Kamlakar
[10 empty] | ME_RW_OPEN-ATTP_DEF | Confirm reporting results in ATTp for opened Master Case | Step 3 | ATTp: Go to event view and confirm that Commissioning, Packing and then Unpacking, Decommissioning events are registered for that Master Case | Events are visible on the event list in correct order. Date and time for events are valid | ITC | Kamlakar
[10 empty] | ME_RW_OPEN-ATTP_DEF | Confirm reporting results in ATTp for opened Master Case | Step 4 | OER: [Optional - depends if SU knows OER solution] Login OER Application server and find the Master Case from Step 2 by putting its sGTIN number into filter | Request executed and Master Case found successfully in OER data | ITC | Kamlakar
[10 empty] | ME_RW_OPEN-ATTP_DEF | Confirm reporting results in ATTp for opened Master Case | Step 5 | OER: [Optional] - Check events list for that container - confirm that Packing, Unpacking events were registered and they are assigned to your factory correctly | Events list is correct, date/time is valid | ITC | Kamlakar
[10 empty] | ME_RW_OPEN-ATTP_DEF | Confirm reporting results in ATTp for opened Master Case | Step 6 | OER: [Optional] - Go to 'Current Hierarchy' view and confirm that MC is not assigned to any OUT (as a Parent) | Hierarchy list displayed correctly - no links to other containers | ITC | Kamlakar
ME-SIT-OTH-08 | Other ME | GENERIC | Destroy a previously registered Case in ME area (Destroy All transaction on APRISO ME T&T HH) | N | X | -Elective, Pack level tracking SKU -FMC [Cigarettes material group] -End Market - China and domestic/Malaysian, produced in Malang, ID -Standard communication with FSS3, ATTp to be tested -containers [full MC] to be produced with METS Simulator, but barcodes for scanning with real HH device must be printed on a paper -for the above action, local SU support is required | Data: 1 Elective or Legal SKU with Pack Level Tracking indicator; Process: Master Case produced on T&T production line - product quality issue noticed and decision made for the whole product destruction; Systems: FSS3: Master Case created on the line for T&T SKU and reported successfully to FSS3 by Line System APRISO ME T&T HH: Device available and communication with FSS3 application is established ATTP: Aggregation for the created Master Case for T&T SKU recored and reported successfully to Authorities [if required] | Due to quality (or any other) issues, Master Case produced in ME area (but not GRed yet) is fully decommissioned with Destroy All transaction on APRISO ME T&T HH and then physically destroyed (including Packs). PK & OUT & MC IDs must not be used in any other aggregation. | Destroy event for MC and its children is reported successfully to ATTp | ME_DESTRU_DESTROYALL-APRISO-HH_DEF | Destroy All (Transaction on APRISO ME T&T HH) on the registered Case with ME T&T HH | Step 1 | ME-Destruction area: Prepare 1 Master Case which has to be fully destroyed with its content | Master Case prepared and ready for destruction | ITC | Kamlakar
[10 empty] | ME_DESTRU_DESTROYALL-APRISO-HH_DEF | Destroy All (Transaction on APRISO ME T&T HH) on the registered Case with ME T&T HH | Step 2 | ME-HH: Login Apriso application and check if Destroy All transaction is visible in main menu | Successfull ME HH login and Destroy All transaction is available for usage | EM
[10 empty] | ME_DESTRU_DESTROYALL-APRISO-HH_DEF | Destroy All (Transaction on APRISO ME T&T HH) on the registered Case with ME T&T HH | Step 3 | ME-HH: Run Destroy All transaction and scan Master Case label (the one that has to be destroyed) | Destroy All transaction launched and Master Case ID accepted | EM
[10 empty] | ME_DESTRU_DESTROYALL-APRISO-HH_DEF | Destroy All (Transaction on APRISO ME T&T HH) on the registered Case with ME T&T HH | Step 4 | ME-HH: Click the right arrow button to confirm Master Case ID | Warning for destruction's result has been displayed | EM
[10 empty] | ME_DESTRU_DESTROYALL-APRISO-HH_DEF | Destroy All (Transaction on APRISO ME T&T HH) on the registered Case with ME T&T HH | Step 5 | ME-HH: Click the right arrow button again, this time to finalize operation and fully decommission Master Case and its content | Operation completed successfully, no error displayed | EM
[10 empty] | ME_DESTRU_DESTROYALL-ATTP_DEF | Confirm reporting results in ATTp for Master Case destroyed in ME area | Step 1 | ATTp: Login ATTp platform and go to Serialized containers/items transaction/view | Successfull login to ATTp, no issues with access to Serialized containers/items | ITC | Kamlakar
[10 empty] | ME_DESTRU_DESTROYALL-ATTP_DEF | Confirm reporting results in ATTp for Master Case destroyed in ME area | Step 2 | ATTp: Find the Master Case destroyed in the previous steps by filling filters with MC's Serial Number and Plant Number, and then click 'Run'/'Execute' | Destroyed MC is found successfully in ATTp and its production details are displayed on the screen | ITC | Kamlakar
[10 empty] | ME_DESTRU_DESTROYALL-ATTP_DEF | Confirm reporting results in ATTp for Master Case destroyed in ME area | Step 3 | ATTp: Go to event view and confirm that Unpacking, Decommissioning events are registered for that Master Case | Events are visible on the event list in correct order. Date and time for events are valid | ITC | Kamlakar
[10 empty] | ME_DESTRU_DESTROYALL-ATTP_DEF | Confirm reporting results in ATTp for Master Case destroyed in ME area | Step 4 | ATTp: [Optional] Check the response from authorities for the messages from the previous step | Repsonse messages indicate 'OK' | ITC | Kamlakar
[10 empty] | ME_DESTRU_DESTROYALL-ATTP_DEF | Confirm reporting results in ATTp for Master Case destroyed in ME area | Step 5 | ATTp: Go to hierarchy view for that Master Case and confirm that Outers are displayed and all of them has destroyed disposition visible | Containers list is full - Outers IDs are visible | ITC | Kamlakar
[10 empty] | ME_DESTRU_DESTROYALL-ATTP_DEF | Confirm reporting results in ATTp for Master Case destroyed in ME area | Step 6 | OER: [Optional - depends if SU knows OER solution] Login OER Application server and find the Master Case from Step 2 by putting its sGTIN number into filter | Request executed and Master Case found successfully in OER data | ITC | Kamlakar | Pending for Execution
[10 empty] | ME_DESTRU_DESTROYALL-ATTP_DEF | Confirm reporting results in ATTp for Master Case destroyed in ME area | Step 7 | OER: [Optional] - Check events list for that container - confirm that Destroyed disposition was registered and it is assigned to your factory correctly | Events list is correct, date/time is valid | ITC | Kamlakar | Pending for Execution
ME-SIT-PAL-12 | Palletization | GENERIC | Build a Pallet manually (Palletize transaction on APRISO ME T&T HH) | N | X | -Elective, Pack level tracking SKU -FMC [Cigarettes material group] -End Market - China and domestic/Malaysian, produced in Malang, ID -Standard communication with FSS3, ATTp to be tested -containers [XX full MCs] to be produced with METS Simulator, but barcodes for scanning with real HH device must be printed on a paper -new SSCC label must be pre-printed -for the above action, local SU support is require | Data: 1 Elective or Legal SKU with Pack Level Tracking indicator; 1 Production Order in TaO; Process: Relevant number of Master Cases produced on T&T production line - quantity depends on UAT preparation agreement - if it will be number of a full standard Pallet or smaller for local team convenience; Systems: FSS3: Master Cases created on the line for T&T SKU and reported successfully to FSS3 by Line System APRISO ME T&T HH/Scanner: Device available and communication with FSS3 application is established ATTP: Aggregations for the created Master Cases for T&T SKU recored and reported successfully | Pallet built manually with APRISO ME T&T HH; as result Pallet Aggregation message is reported to FSS3 and then after successfull validation, Pallet Aggregation is reported to ATTp. | Success message displayed on APRISO ME T&T HH. Pallet aggregation recorded in ATTp. | ME_PAL_PAL-BUILD-APRISO-HH_MANUAL | Manual Palletization done with ME T&T HH/Scanner | Step 1 | ME-HH: Login Apriso application and check if Palletize transaction is visible in main menu. Run that transaction | Functionality dedicated for a new Pallet built is available. Transaction successfully launched | EM
[10 empty] | ME_PAL_PAL-BUILD-APRISO-HH_MANUAL | Manual Palletization done with ME T&T HH/Scanner | Step 2 | ME-HH: Scan Master Cases [labels] which have to be palletized | All Master Case labels scanned successfully, system navigates automatically to next screen | EM
[10 empty] | ME_PAL_PAL-BUILD-APRISO-HH_MANUAL | Manual Palletization done with ME T&T HH/Scanner | Step 3 | ME-HH: Scan a new pre-printed SSCC label which will be assigned to that Pallet and then confirm the step by clicking the right arrow | The new pre-printed SSCC label scanned successfully, transaction confirmed and Pallet ID accepted - no errors displayed | EM
[10 empty] | ME_PAL_PAL-BUILD-APRISO-HH_MANUAL | Manual Palletization done with ME T&T HH/Scanner | Step 4 | FSS3: [Optional - depends if IT SU knows how to work in FSS3 Apriso Desktop Client] Login FSS3 application server and open Apriso Desktop Client application | Successfull FSS3 app server login | ITC | Prasanth
[10 empty] | ME_PAL_PAL-BUILD-APRISO-HH_MANUAL | Manual Palletization done with ME T&T HH/Scanner | Step 5 | FSS3: [Optional] Login into Apriso Desktop Client with your credentials and go to Immediate Job History | SU credentials accepted and Apriso Desktop Client launched without issues | ITC | Prasanth
[10 empty] | ME_PAL_PAL-BUILD-APRISO-HH_MANUAL | Manual Palletization done with ME T&T HH/Scanner | Step 6 | FSS3: [Optional] Find the new hierarchy message for the Pallet created in Step 3 (for example by filtering messages list with Pallet Serial Number) | The Pallet hierarchy messages found | ITC | Prasanth
[10 empty] | ME_PAL_PAL-BUILD-APRISO-HH_MANUAL | Manual Palletization done with ME T&T HH/Scanner | Step 7 | FSS3: [Optional] Check and confirm that Pallet hierarchy message was received by FSS3 and processed successfully | Message found in the Step 8, processed by FSS3/Apriso without errors | ITC | Prasanth
[10 empty] | ME_PAL_PAL-BUILD-ATTP_DEF | Confirm reporting results in ATTp for Pallet built on ME area | Step 1 | ATTp: Login ATTp platform and go to Serialized containers/items transaction/view | Successfull login to ATTp, no issues with access to Serialized containers/items | ITC | Prasanth
[10 empty] | ME_PAL_PAL-BUILD-ATTP_DEF | Confirm reporting results in ATTp for Pallet built on ME area | Step 2 | ATTp: Find the created Pallet by filling filters with PAL's Serial Number (SSCC) and Plant Number, and then click 'Run'/'Execute' | Registered PAL is found successfully in ATTp and its production details are displayed on the screen | ITC | Prasanth
[10 empty] | ME_PAL_PAL-BUILD-ATTP_DEF | Confirm reporting results in ATTp for Pallet built on ME area | Step 3 | ATTp: Go to event view and confirm that Packing event is registered for that Pallet (SSCC) | Event is visible on the event list in correct order. Date and time for event are valid | ITC | Prasanth
[10 empty] | ME_PAL_PAL-BUILD-ATTP_DEF | Confirm reporting results in ATTp for Pallet built on ME area | Step 4 | ATTp: [Optional] Check the response from authorities for the message from the previous step | Repsonse message indicate commissioning and packing 'OK' | ITC | Prasanth
[10 empty] | ME_PAL_PAL-BUILD-ATTP_DEF | Confirm reporting results in ATTp for Pallet built on ME area | Step 5 | ATTp: Go to hierarchy view for that Pallet and confirm that Master Case list is displayed | Containers list is full - Master Case IDs are visible | ITC | Prasanth
[10 empty] | ME_PAL_PAL-BUILD-ATTP_DEF | Confirm reporting results in ATTp for Pallet built on ME area | Step 6 | OER: [Optional - depends if SU knows OER solution] Login OER Application server and find the Pallet from Step 2 by putting its sGTIN number into filter | Request executed and Pallet found successfully in OER data | ITC | Prasanth
[10 empty] | ME_PAL_PAL-BUILD-ATTP_DEF | Confirm reporting results in ATTp for Pallet built on ME area | Step 7 | OER: [Optional] - Check events list for that container - confirm that Packing event was registered and it is assigned to your factory correctly | Events list is correct, date/time is valid | ITC | Prasanth
[10 empty] | ME_PAL_PAL-BUILD-ATTP_DEF | Confirm reporting results in ATTp for Pallet built on ME area | Step 8 | OER: [Optional] - Go to 'Current Hierarchy' view and confirm that PAL hierarchy is fully visible, so PKs are linked to OUTs and the OUTs to MCs and the MCs to the PAL | Hierarchy list displayed correctly , no issues with Pallet hierarchy | ITC | Prasanth